## Sheet1
Story ID | Module | Story Name | Description | Priority | Iteration | Acceptance Criteria | Notes | Point | Date Started | Date Finished
E02.1 | manage | modify personal information | as a student, I want to modify my personal information in the record, so that I can update my outdated personal information | very high | 1 | 1, verify that The corresponding outdated information is completely removed. 2, verify that The corresponding updated information is fully stored (can be viewed) 3. verify that the submitted form is not empty, else Refuse to submit and popup prompt |  | 1 | 2023-03-29 | 2023-03-31
E05.1 | exit | exit the application | as a user, I want to exit the application, so that I can quit to finish my use | very high | 1 | verify that the exit button work to end the program |  | 1 | 2023-03-30 | 2023-03-31
E00.1 | interface | login | as a student, I want to enter my account number and password to log in, so that I can go to my own account | very high | 1 | 1. verify that the user enter account and password; 2. verify the account and password are corresponding; 3. if they 're corresponding, enter the account, if else, refuse the login |  | 1 | 2023-03-30 | 2023-03-31
E02.2 | manage | add new honor | as a student, I want to be free to add my honor, so that I can add my honor information myself | high | 2 | 1. verify that The corresponding information is fully stored (can be viewed) 2. verify that the submitted form is not empty, else Refuse to submit and popup prompt |  | 1 | 2023-04-12 | 2023-04-13
E02.3 | manage | delete existing honor | as a student, I want to delete the honor in the record, so that I can delete the honor I don’t need | high | 2 | verify that The corresponding information is completely removed. (can not be viewed) |  | 1 | 2023-04-12 | 2023-04-13
E03.2 | view | view all grades | as a student, I want to check my course grades, so that I can check my study | view high | 2 | 1. verify that all the course grades are displayed; 2. verify the correct information is displayed |  | 2 | 2023-04-13 | 2023-04-14
E02.4 | manage | add new project | as a student, I want to be free to add my project, so that I can add my project myself | high | 2 | 1. verify that The corresponding information is fully stored (can be viewed) 2. verify that the submitted form is not empty, else Refuse to submit and popup prompt |  | 1 | 2023-04-18 | 2023-04-18
E02.5 | manage | delete existing project | as a student, I want to delete the project in the record, so that I can delete the project I don’t need | high | 2 | verify that The corresponding information is completely removed. (can not be viewed) |  | 1 | 2023-04-18 | 2023-04-18
E03.4 | view | view all honors | as a student I want to view my honors, so that I can present my honors in an intuitive way | view high | 2 | 1. verify all the honors are displayed; 2. verify all the honors are correctly |  | 3 | 2023-04-21 | 2023-04-23
E03.5 | view | view all projects | as a student I want to view my projects, so that I can present my projects in an intuitive way | view high | 2 | 1. verify all the projects are displayed; 2. verify all the projects are correctly |  | 3 | 2023-04-21 | 2023-04-23
E00.2 | interface | welcome | as a student, I want a navigation interface so that I can access all the modules I need clearly and easily | high | 2 | 1. verify that the interface covers all the functions; 2. verify that the interface can jump to correspond function; |  | 3 | 2023-04-12 | 2023-05-02
E03.3 | view | view statistic information | as a student, I want to check my statistic information (GPA and ranking), so that I can check my study | high | 3 | 1. verify the correct information is displayed; 2. varify the algorithm work normally |  | 5 | 2023-05-01 | 2023-05-12
E03.1 | view | view personal information | as a student, I want to check my personal information, so that I can verify the information | view high | 3 | 1. verify the correct information is displayed |  | 1 | 2023-05-04 | 2023-05-04
E02.6 | manage | add new skill | as a student, I want to record my skills in a simple form so that I can integrate all individual skills | high | 3 | 1. verify that The corresponding information is fully stored (can be viewed) 2. verify that the submitted form is not empty, else Refuse to submit and popup prompt |  | 1 | 2023-05-07 | 2023-05-07
E02.7 | manage | delect existing skill | as a student, I want to delete the skill in the record, so that I can delete the skill I don’t need | high | 3 | verify that The corresponding information is completely removed. (can not be viewed) |  | 1 | 2023-05-07 | 2023-05-08
E03.6 | view | view all skills | as a student I want to view my skills, so that I can present my skills in an intuitive way | high | 3 | 1. verify all the skills are displayed; 2. verify all the skills are correctly |  | 3 | 2023-05-08 | 2023-05-09
E03.7 | view | view learning journey | as a student I want to view my learning journey, so that I can I can easily integrate my learning journey in an visual way | middle | 3 | 1. verify all the information is displayed; 2. verify all the information is correct 3. verify the learning journey generate in correct format |  | 8 | 2023-05-02 | 2023-05-13
E00.4 | interface | back page | as a student, I want to have the back button when I use the application, so that I can go back to the previous page | high | 3 | verify the back botton can work to bring the user to the page previous | Try to implement it in all modules | 13 | 2023-05-12 | 2023-05-20
E04.1 | export | export personal data | as a student I want to exporting my personal information, so that I can easily check my personal data. | low | 4 | 1. verify that the file is export in .json 2. verify that the personal information is correctly export; |  | 5 | 2023-05-10 | 2023-05-24
E00.3 | interface | Integrate functions | as a student, I want the module interfaces can integrate its all functions in few pages, so that I can implement the functions I need according to clear logic | low | 4 | 1, verify the functions about the module integrate below 3 pages; 2. verify the functions work as usual | Try to implement it in all modules | 13 | 2023-05-10 | 2023-05-25
We incorporated this functionality into E02-manage
E01.1 | input-record
E01.2 | input-record
E01.3 | input-record